## AJHS
Building Priorities (from list provided)
1 | GoGuardian
2 | Google Suite
3 | Promethean Basics
| Preferred delivery method for staff (may look different for each of your priorities) |  | Meeting 2.12.20
Priority 1 | During a faculty meeting. Have everyone sign in and show them how to use it. We would like some training for ourselves before we open it up to teaching faculty. Follow up with individual teachers to see what problems they are having using it. Additional time for more training as a half day or conference topic. | March faculty meeting | Goal of Google Classroom for all teachers or a Google Sites
Priority 2 | Half day during the March conference day. We could have two different classes offered. One basic and one more in depth | Waiting on agenda | Google Suite/ Classroom focus
Priority 3 | Half day during a school day where the teacher can sign up and get a sub. Have them bring a lesson plan and we can help them incorporate the boards into their lessons. Have 4 boards available in the room, so a small group of teachers can practice hands on use of the board. | Will discuss space and dates at BLT meeting
Meeting dates (Need 3 afterschool meetings)
February 2/12/2020
April 4/22/2020
June 6/3/2020
Timeline (need specific dates) | Goal of this step | What specific PD is being provided? | Roles for team members (Who will be doing what) | Will subs be needed? How many? | What support will you need for this day? Materials, Renee/Tom/Abbie, Space | How will you measure that you met your goal for this step?
End of April | Each teacher will have a Google Classroom. | Teachers will be guided individually or in small groups on creating a classroom. | Based on responses, team members will be assigned to specific faculty. | None, if we can use some time on March 20th, or throughout th eschool day. |  | When every teacher has a Google Classroom presence.
2020-05-28 | Assist Teachers in improving their lessons using Google applications, etc. | Direct Instruction about Google applications./Imrpoving Lesson plans | Lead Sessions | Yes 12 | We need time to meet with Reneeto review what apps we have access to, and how much access.
2020-04-17 | Google Classroom Basics | Direct Instruction about Google applications./Imrpoving Lesson plans | Lead Sessions | Yes.12 | Chromebooks. | Use Google Forms for teacher feedback.
March 20th | 4 Concurrent sessions. Two Go Guardian and Two Classlink. | Two sessions of leveled Go Guardian. Lower: create classes, scheduling sessions, monitoring tabs.
|  | Higher Level: Above plus Scenes. | Julie Advanced Go G, Danielle Basic Go G
|  | Two introductory Classlink Sessions. | Deb and Kelly Sue "Classlink"

## Casey Park
Building Priorities (from list provided)
1 | Promethean Basics
2 | Google for Education Basics
3 | GoGuardian Usage
Preferred delivery method for staff ( may look different for each of your priorities)
Priority 1 | Staff interested would sign up for a Promethean Basics Refresher. We will push out a Google sign up for time blocks and we will teach basics during that time block. We would need 6 subs to rotate through classrooms. Staff would come in one hour shifts.
Priority 2 | We could do a training during the half day in March. Trainers could meet with teachers during the PD day to implimize Typing Club in the classroom.
Priority 3 | GoGuardian: Could be delievered during a Staff faculty meeting (15 minutes)
Priority 4 | Google for the Classroom
Meeting dates (Need 3 afterschool meetings)
February 24, 25, 27
April 20, 21, 22
June 15, 16, 17
Timeline (need specific dates) | Goal of this step | What specific PD is being provided? | Roles for team members (Who will be doing what) | Will subs be needed? How many? | What support will you need for this day? Materials, Renee/Tom/Abbie, Space | How will you measure that you met your goal for this step?
March 20th Staff Development Day | Go Guardian / Class Link for All Staff | Implement what Go Guardian is based on District training and expectations | Kiley and Shannon will present Go Guardian and provide handouts with step by step instruction. We will then have staff log in and set up classrooms. | No Subs needed | No Support Needed | Google Form on specific questions on Staff useage with Go Guardian
March 20th Staff Development Day | Typing Club (what typing club is, how kids log in, what it looks like from a students perspective, discus integration into classroom, teacher access reports to monitor progress | An over view of typing club. What typing club is and a students perspective. Discuss ways to incorporate typing club into a daily or weekly scheduled time for each grade level. | Kiley, Penny and Shannon will present to staff in small groups | No Subs Needed | All Casey Park Staff need Typing Club Accounts | Exit Ticket on Promethean Board on how each Teacher plans on using it in the classroom
April 14th & 15th | Promethean Refresher | Based on Google Form we will address basic use of Promethean Board use and applications. Getting 100% basic board use. | Kiley and Shannon will present and provide handouts with step by step instruction and a powerpoint on Promethean Use. | 5 Subs are need for the entire day. Kiley and Shannon will alternate days / times of instruction based on staff needs, skill set and comfertability. | No Support Needed | March 20th Staff Day fillout the Promethian & Digital Basic Google Form. Post Survey on a checklist of what basic functions they use daily. | 40 minutes each groups based on their surveys - look at survey - results - Survey given on March 20th
May 12th | Google for the classroom | What Google classroom is, how it can be used in the classroom and how to set up a class or assignments | Kiley and Shannon will present and provide step by step instruction how to use google classroom, setting up students and assignments, how to incorporate it into assorted curriculum. | 5 Subs are need for the entire day. Kiley and Shannon will alternate days / times of instruction based on staff needs, skill set and comfertability. | No Support Needed | Have teachers set up a test classroom or test assignments
March PD Day | (1) 15 minute session of time to add class names for google classroom (2) 40 Minute Sessions: GoGuardian (2) 40 Minute Sessions: Class Link 15-20 Minute (3 Groups): Typing Club | Locations: Library Innovation Lab | K-2 & Specials, AIS: Kiley 3-6: Shannon Typing Club: Shannon, Kiley & Penny

## Herman
Building Priorities (from list provided)
1 | Promethean Basics / Review
2 | ActivCast / Classflow / ActivInspire
3 | GSuite - Basics - Exposure Level if necessary (Gmail, drive, Docs-Sheets
Preferred delivery method for staff ( may look different for each of your priorities)
Priority 1 | Faculty Meeting, Video Push, Before or After School meeting
Priority 2 | ActivCast: Video Push with follow up support. For Classflow and ActivInspire the committee will make available time during the day by appointment, Staff Development Day, and Faculty Meeting highlights.
Priority 3 | Staff Development Time, Faculty Meeting Options, by appointment to one of the team memebers, and if necessary through video tutorial.
Meeting dates ( Need 3 afterschool meetings)
feb- 26th, 3:15-3:45
April- 15th, 3:15-3:45
June- 10th, 3:15-3:45
Timeline (need specific dates) | Goal of this step | What specific PD is being provided? | Roles for team members (Who will be doing what) | Will subs be needed? How many? | What support will you need for this day? Materials, Renee/Tom/Abbie, Space | How will you measure that you met your goal for this step?
3/5-6/5 | For teachers to input the use of typing club into the classroom for a target of 30 minutes a week per student. | none | Michelle and Meg will track and review the data monthly | no | Setting Meg up with an account so she can view student data | By reviewing the data and communicating with teachers based on that data.
2020-03-20 | Offer training to staff on using Classflow and ActivInspire by ogranizing a set time block during the upcoming staff development day pending approval of building principal | none | Team members will communicate and offer time slots for the educators to sign up for pending team organization of time slots | no | none | Collecting numbers on sign ups slots and attendance numbers | innovation lab and library - still determining who will do which - need to get final dates and a plan together
2/28-3/13 | Send out a survey to all of the staff regaurding the use of technology and specific applications | will depend on results | Steve will collect and organize the data and together he and Meg will prioritize and plan for further trainings | none | none as of now | Once we go over all of the results we will be able to plan trainings and offer better and more specific support
3/13-6/5 | Based on survey results, specific trainings on technology software and hardware will be provided to individual staff geared toward individual needs. | depends on results | Meg and Steve will team together to meet with staff members and provide assistance as needed. | depends on the level of need and intensity of the need | none | Keep tickets of who we meet with and how we assisted them
Day 2 and 5
Talking about Google Classroom at 3/5 Faculty Meeting
Possibly having one of the workshops be everyone while others be sign up

## Owasco
Building Priorities (from list provided)
1 | Google for Education
2 | Promethean Board
3 | Software
Preferred delivery method for staff ( may look different for each of your priorities)
Priority 1 | Survey what features of Google for Education are needed/ wanted. (Classroom, sites, drive, Assistive technology). Using a scaffolding approach (beginner to advanced) to offer what needs to be supported. PD days. Could PLC time be used? Using my flex time to go into classes. | Each teacher having one of the following prior to the end of the school year: Google Classroom, Google site. Team will look at creating a site template for uniformity. Team will inquire about the use of PLC time or Faculty meeting to achieve this goal ASAP.
Priority 2 | Having teachers go beyond the basics. Survey teachers for what is the priority. Introducing advanced features in Faculty meeting. Follow up with PD during PD days. Could PLC time be used? | Scaffolded PD day set up in the building tiered opportunities
Priority 3 | Software basics (Windows 10), app extensions with an emphasis on Go Guardian for student monitoring. How to turn extensions off tends to be an issue. Survey what is needed. PD days. Could PLC time be used? | Go Guardian training as a priority
| Meeting dates | Feb 10th, April 28th, June 8th
Timeline (need specific dates) | Goal of this step | What specific PD is being provided? | Roles for team members (Who will be doing what) | Will subs be needed? How many? | What support will you need for this day? Materials, Renee/Tom/Abbie, Space | How will you measure that you met your goal for this step?
March 5th | Inform Owasco Faculty of primary goal: Google Classroom/ Google Site100% on board | Faculty will be informed of support of SCEP goal of effective communication with parents by utilizing the parent invite of Google Classroom or a website presence. | Whitney and Christina present | 0 | Time during faculty meeting | Present the information to look at creating a site template for uniformity for all staff awareness
2020-02-27 | Creation of Owasco Elementary Google Site Template | Whitney and Christina will create a template for Owasco to use for their websites | Whitney and Christina present | 0 | Time during prep | Creating a template and submitting to https://support.google.com/a/answer/166430?hl=en
March 25th,26th and 30th | Hands on with faculty to create websites/ instructional time and work time | Teachers will be given instruction on creating websites in Google and then given time to create their own | Whitney and Christina present | 3 on 3/25, 4 on 3/26, 3 on 3/30 | Approval and roll out of the template. Reserve the computer lab | Either Google classroom code will be given to admin or link to created website.
2 Hour Google Sign Ups
Post 3/30 | Survey Staff about Promethean training needs | Scaffold next round of training for beginning, intermediate, and advanced use of Promethean Board tools and apps | Whitney and Christina will create a Google Form for survey | 0 |  | Analyze data from the survey to set up next goal and PD to be provided
April | Implement training needs for Promethean Board use | Pending Survey results (basic needs to use of different apps and programs) | Whitney and Christina present | 3 days with 3 subs, 4 subs, and 3 subs | Approval. Reserve the computer lab
March 20 Whitney will be training in Go Guardian and Chris will be doing the training in ClassLink. Chris will be using the library and Whitney will be using the lab. There is not a Promethean board in there but we will be asking for access to one to be brought down to present. Or I may possibly just use another classroom that accommodates half of the staff. We are going to figure out at a later date how we are going to split the staff, but we are looking at having them move rooms when it is time to switch.

## AHS
Building Priorities (from list provided)
1 | Google Classroom - different levels/departments
2 | GoGuardian
3 | App Share
| Preferred delivery method for staff ( may look different for each of your priorities) | Agenda questions for 2/3 meeting | Minutes from 2/3/2020 - Next steps
Priority 1 | Using a faculty meeting and survey to relay information about the Ed Law 2D, our roles in the district, and our goal to have all teachers create a Google Classroom for the 2020-2021 school year regardless of courses and content area. | February Faculty meeting, Questions - how many have them now? Goal for this year? Goal of all fo next year? How are we going to tracking or monitor this ? What model do we want to use to show teachers more about Google Classroom | March - Groups Admin available in each meeting. Survey Google Classroom, Google Sites April - finish google classrooms or GoGuardian - Goal - BY June 30th all staff will have evidence of starting the design process of their classroom.
Priority 2 | Use staff development day/designated faculty meeting/optional after school sessions to teach designated apps | Waiting on agenda for the March PD day. What specific apps are you looking to share?
Priority 3 |  | Go-Guardian - when/ how do we want to present to staff?
Meeting dates
2/3/2020 - 2:50
4/20/2020 - 2:50
6/1/2020 - 2:50
Timeline (need specific dates) | Goal of this step | What specific PD is being provided? | Roles for team members (Who will be doing what) | Will subs be needed? How many? | What support will you need for this day? Materials, Renee/Tom/Abbie, Space | How will you measure that you met your goal for this step?
2020-03-05 | To use the results from our survey to create groups of teachers in Labs to give tutorials and work time building a Google Classroom or Google Site | To get teachers to determine which of the two platforms would best benefit their classroom and give assistance in creating, setting up, or advancing their understanding using the platform in their classrooms | Kelley will be working with beginners on Google Classroom, Lizzie will be working with intermediate level for Google Classroom, Allison will be working with advanced level Google Classroom users, and Christina will work with anyone interested in creating a Google Site (2:45 - 3:30) | No. | Use of 4 different labs, teachers have access to content digitally, administrator in each lab | Each person will digitally respond to the progress they made during their session, what they actually did, and what additional questions or hopes they have.
2020-03-20 | Follow up with the chosen platform and GoGuardian | Assistance with further development of the Google platform of choice. (Science department will be out of the building this afternoon doing NGSS training) | Each member available will on call and/or moving around the building to support teachers in their own classrooms during a specific building time (1:00-2:50 pm) | No. | Having Tom or Renee availble by phone with questions or troubleshooting if needed. | Each person will digitally respond to the progress they made during their session, what they actually did, and what additional questions or hopes they have.
2020-04-02 | Using a faculty meeting time to have specified teachers share a specific app or website they have used in their classroom, and non-presenters will attend a presentation of their choice to view, and they begin to create their own lesson or use of the program in theri classroom. | Sharing of app and website use in classrooms, lessons, etc. then creating or exploring the use of this app or website in a classroom that has never used it before. | Present how an app or website has been used in the classroom, show evidence, talk about pros and cons, student reponse to the app or website, and how it has improved instruction, grading, access, etc for the students, teachers, or class. (2:45-3:30) | No. | Use of 4 different labs, teachers have access to content digitally, administrator in each lab | Each person will digitally respond to the progress they made during their session, what they actually did, and what additional questions or hopes they have.
2020-05-07 | Create a culture of sharing out of progress made using technology in the classroom | Teachers are sharing out what they are using, and how it benefits teachers, students, and/or community members. Two teachers from each department will take no more than 3 to 5 minutes presenting on or two apps or websites they are using and demonstrate how they support the learning and classroom. Departments to present at this meeting would be (Art, music business etc/English/Math/Other/PE). | Giving support and making ourselves available leading up to this, and all meetings involving the use of technology and improving comfort levels for integrating technology to support the learning of our students. | No. | Promethean board, laptop to assess a website if needed, etc. Depending on who is presenting and what will be presented. Teachers must submit what they are presenting prior to the meeting so all necessary items are available. | We will record what apps each group presented and if other teachers have questions about these apps, they can ask the building leaders or the teacher(s) who presented them.
2020-06-04 | Create a culture of sharing out of progress made using technology in the classroom | Teachers are sharing out what they are using, and how it benefits teachers, students, and/or community members. Two teachers from each department will take no more than 3 to 5 minutes presenting on or two apps or websites they are using and demonstrate how they support the learning and classroom. Departments to present at this meeting would be (Science, Social Studies, Special Education, Technology, and World Languages). | Giving support and making ourselves available leading up to this, and all meetings involving the use of technology and improving comfort levels for integrating technology to support the learning of our students. | No. | Promethean board, laptop to assess a website if needed, etc. Depending on who is presenting and what will be presented. Teachers must submit what they are presenting prior to the meeting so all necessary items are available. | We will record what apps each group presented and if other teachers have questions about these apps, they can ask the building leaders or the teacher(s) who presented them.
Next Meeting: Thurs. 2/27 2:25pm

## Genesee
Building Priorities (from list provided)
1 | Utilizing Interactive Displays- with Grade Level Focus
2 | Google for Education- specifcally Docs, Classroom
3 | Software- tools in general
| Preferred delivery method for staff ( may look different for each of your priorities) |  | 2.12.20 Meeting Minutes
Priority 1 | Tech. Mentors get full day release to meet with grade level teams for 1-2 hours each. Floating subs will be provided for the day and they will rotate between grade levels. 3 subs will be needed and a schedule will need to be created. Grade level teachers will be surveyed prior to find out specific needs. | Yes let's work with Heather to select a day that works for the building | GoGuardian, Google Classroom/Site, promeathen basics
Priority 2 | A scope and sequence for Google tools needs to be created. (i.e.- by the end of 2nd grade, students will know how to create and open a Google Doc). The goal is that the librarian will introduce Google tools (Docs, etc.) and communicate with teachers when skills are taught. Teachers will incorporate tools in the classroom after they have been taught in library. Teachers will be able to incorporate these tools into their existing curriculum. This can take place at librarian meetings/ District Level Digital Teaching and Learning Team Meetings. | We will be addressing this on Feb 26th at that meeting
Priority 3 | We will compile a list of which tools are compatible with which software (i.e. Extensions, apps). We will present this information at an upcoming faculty meeting or during the March Staff Development Day. If teachers would like specific "training" on how to use a tool, they will be shown during this time how they can create a Help Ticket. | Renee will reach out to start helping with the list. Still waiting on agenda for March Day. | what do teacher want students to learn? Then give the tool to support tool
Meeting dates ( Need 3 afterschool meetings)
February- Wednesday, February 5th 3:30-4:00
April- Wednesday, April 15th 3:30-4:00
June- Wednesday, June 3rd 3:30-4:00
Timeline (need specific dates) | Goal of this step | What specific PD is being provided? | Roles for team members (Who will be doing what) | Will subs be needed? How many? | What support will you need for this day? Materials, Renee/Tom/Abbie, Space | How will you measure that you met your goal for this step?

## Seward
Building Priorities (from list provided)
1 | - get more teachers on board with ClassFlow
2 | - teacher the K-2 teachers more things students can do with the boards
3 | - time when teachers can observe lessons done using technology
| Preferred delivery method for staff ( may look different for each of your priorities) | Presentation Topics | Minutes from 2/11/20
Priority 1 | - having a faculty meeting where someone presents ClassFlow | ClassFlow Activities: matching, sequencing, crossword, etc. | Standing agenda item for all faculty meetings
Priority 2 | - half-day training on one of the superintendent's days | Waiting on the agenda | waiting agenda
| - offer three sessions for three different tech-related skills and teachers will come prepared with lessons they might want to present using technology | 1. GoGuardian 2. Promethean Board Tools 3. Google Extensions | GoGuardian - for all teachers with a chromebook in their romo
Priority 3 | - Have a day/week when a teacher is delivering a tech-related lesson and other teachers can come in during prep or with sub coverage to watch the lesson to get ideas and become familiar with the technology, using the building sub as coverage | 1. ClassFlow Lesson 2. FlipGrid 3. ActivInspire 4. Gimkit 5. Quizizz 6. Quizlet 7. ClassDojo (Need to look at instructional priorities) Can discuss the subs set up at BLT | 9 - 13th Morning 10:30 - 12:10 -classflow split the block in half - block Laura
Meeting dates ( Need 3 afterschool meetings)
February 11th at 7:45
April 1st at 7:45
June 2nd at 7:45
Timeline (need specific dates) | Goal of this step | What specific PD is being provided? | Will subs be needed? How many? | What support will you need for this day? Materials, Renee/Tom/Abbie, Space | How will you measure that you met your goal for this step? | Roles for team members (Who will be doing what)
3/9/20-3/13/20 | Show staff how class flow can be used in the clasroom. | Staff will be allowed to come into Beccas classroom from 10:30 to 12:00 monday through Friday to observe how classflow can be used during a lesson. It will show many of the features that class flow offers | Yes. 1. Amy has secured. | the internet to work :) | Staff will able to ask questions to teacher as well as students. Additionally, there will be an additonal training for all staff on 03/20th. | Becca will teaching the lesson while fellow staff memebers wil be able to observe and engage with my students an ask questions.
2020-03-20 | 1. To have staff create a class flow lesson. 2. To expose staff to go guardian and all of its features. | This will be a two 45 minutes sessions that all staff will attend as part of the staff development day. One session will be devoted classflow. Staff wil be exposed to the features of classflow and then will be asked to create a classflow lesson that they will use in the future. The second session will be devoted promeathan boards and google tools | No | Nothing | 1. Staff creating a class flow lesson. 2. Promeathan Board and google tools | AM: 10:30- Mike and Brandon go guardian in mikes room Becca- class flow in her room PM: Becca will be doing classflow and Brandon and Mike will be doing promeathan and google tools.
Future faculty Meetings 3/5 4/2 5/7 6/4 | expose staff to new online resources 3/5- Gimkit 4/2- Quizlet Live 5/7- Quizziz 6/4- ? | show a new tool to staff at each remaining staff meeting. examples: gimkit, quizziz, quizlet, etc | no | nothing | follow up survey with a google form. Also, offer time for staff to come to classrooms and observe again how it is used in a classroom. | Becca, Mike, and Brandon will lead each activity.
Future PD | Generate PD offering based on follow up surveys from 3/20 PD | possible ides: more go guardian training more class flow training | no | Nothing |  | Becca, Mike, and Brandon will lead each activity.